## Activity Log
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | Yes | EXAMPLE
12 | 2023-07-31 | First Zoom call | 1 hour | Ulyana/Hannah/Lisa/Xian | Yes | Shared ideas and interests. Discussed ULEZ idea.
12 | 2023-07-31 | Creating Trello |  | Lisa | Yes
12 | 2023-08-01 | Background research on ULEZ. Thinking of research question. | 2 hours | Hannah | Yes
12 | 2023-08-03 | GitHub repository |  | Lisa | Yes
12 | 2023-08-04 | Doing homework and GitHub push | 4 hours | Ulyana/Hannah/Lisa/Xian | Yes
13 | 2023-08-08 | Card on Trello with the plan initial and expanded ULEZ, timeline. Also copied manually all sites from London Air into pages file so we can see what is open/closed, sites codes etc |  | Ulyana | Yes | This file with data gathered manually is not used, but it helped us to know datasource better
13 | 2023-08-10 | Second Zoom call | 1 hour | Ulyana/Hannah/Lisa/Xian | Yes | Discussed division of tasks and how to start with data collection
13 | 2023-08-11 | Jira timeline and tasks | 30 minutes | Hannah | Yes | Assigned data collection tasks
13 | 2023-08-13 | Card on Trello with the map of ULEZ boundaries and sites, manually picked open sites for initial ULEZ | 6 hours | Hannah/Ulyana | Yes | This file with data gathered manually is not used, but it helped us to know datasource better
14 | 2023-08-14 | Third Zoom call | 1 hour | Ulyana/Hannah/Lisa/Dhara | Yes | Told Dhara about the project and where we were at. Xian did not attend
14 | 2023-08-15 | Downloaded manually from all sites in initial ULEZ NO2 data, shared folder with csv for each site | 4 hours | Ulyana | Yes | Realised it is too time consuming, need to look for another way
14 | 2023-08-17 | Found API page http://api.erg.ic.ac.uk/AirQuality/help and checked if there are links to get all sites and then daily average of NO2. Checked it with Postman app. Found the link with sites, but not with daily average NO2. Explored page https://www.londonair.org.uk/london/asp/datadownload.asp and https://www.londonair.org.uk/london/asp/datasite.asp?site=BL0 via Inspected Element found a link to get daily avarage for NO2. Wrote Python file sites.py to extract all sites. All extracted sites saved to sites.tsv. Google Colaboratory file ULEZ_project_collect_clean created. | 5 hours | Ulyana | Yes
14 | 2023-08-17 | Experiemented with OpenWeather to pull pollution and/or weather data. Looked for API to gather historical weather data. OpenAI had one but subscription only https://openweathermap.org/history Researched and found Meteostat which had API and Python library https://meteostat.net/en/ | 4 hours | Hannah | Yes | Proceeded with Meteostat as Python library
14 | 2023-08-18 | Cleaning and preprocessing initial ULEZ sites to use them with the second API to extract daily average of NO2 for these sites (working with columns, their order, date type, including boroughs which are in initil ULEZ, checking longitudes and latitudes, opened and closed dates) | 5 hours | Ulyana | Yes
14 | 2023-08-19 | Cleaning and preprocessing expanded ULEZ sites to use them with the second API to extract daily average of NO2 for these sites. Getting all data with daily average of NO2 from the second API (wrote Python file no2_ulez.py and all data saved to no2_in_ulez.csv and no2_exp_ulez.csv) | 5 hours | Ulyana | Yes
14 |  | Initial cleaning of NO2 data for initial and expanded datasets (adding info from sites dataframe, working on column's name and order, date type) | 3 hours | Ulyana/Hannah | Yes
14 | 2023-08-20 | Progress report. Ulyana shared preprocessing steps. Hannah added meteo data to NO2 data and saved it to merged files, plus GitHub upload | 5 hours | Ulyana/Hannah | Yes | Had not heard from Dhara or Xian. Lisa on holiday.
15 | 2023-08-21 | Cleaning and reorganising the merged data for initial and expanded ULEZ (removing duplicate and renaming columns, date type, giving description to colomns, choosing ratified rows, checking rows with Nan, dropping Nan, dropping irrelevant columns) | 8 hours | Hannah/Ulyana | Yes
15 | 2023-08-22 | Analysis and visualisations (line, histogram, box, bar, scatter plot, correlation heatmap, summary statistics) for initial and expanded ULEZ, map (tried different approacges to get London map with ULEZ on it, choropleth maps with NO2 average by borough by year, choropleth maps with NO2 average by borough before ULEZ, after ULEZ) | 15 hours | Hannah/Ulyana | Yes
15 | 2023-08-22 | Catching up on what was done with data gathering and preprocessing. Conducting exploratory data analysis using the files that the team created. | 2 hours | Lisa | Yes
15 | 2023-08-23 | Tried a few models (regression) | 4 hours |  | Yes
15 | 2023-08-24 | Adding line graphs to see the impact between the initial boroughs and time series forecast for initial and expanded ULEZ | 2 hours | Lisa | Yes
15 | 2023-08-25 | PDF writing - Hannah, organising files - Ulyana, writing analysis - Lisa, Zoom meeting | 6 hours | Hannah/Ulyana/Lisa | Yes
15 | 2023-08-25 | Adding descriptive comments to plots in the analysis file | 1 hour | Lisa | Yes
15 | 2023-08-26 | Writing PDF, README file, combining logs, working on expanded ULEZ visualisation, analysis and forecast file | 6 hours | Hannah/Ulyana | Yes
15 | 2023-08-27 | Final checks, uploading files into Github and creating pull request | 1 hour | Lisa | Yes
Note: On average for the last two weeks (14 to 27 August) Hannah and I (Ulyana) spent around 5 hours a day every day on project work. We did not have enough time to log everything we had done, the log is approximation.